## Roadmap
BLUE = ONGOING PROJECTS | RED = PROJECTS BEHIND SCHEDULE / CANCELATIONS | [10 empty] | LIGHT GREEN = COMPLETE
GREEN = COMPLETE PROJECTS | YELLOW = NEEDS ATTENTION
2021-23 NLA Roadmap | 2021 JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | 2022 JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | 2023 JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE
NLA Administration, Processes & Structure
Committee Strategic Plan | Adopted |  | Present roadmap to committee |  |  |  |  | APRIL: Revisit; NOVEMBER: Revisit, Begin planning for next biennium
Council Check-in | Suggested: Land Use Education Plan Accomplishments |  |  | Suggested Recommendation: None. |  |  | Suggested Recommendation: Climate Friendly & Equitable Communities Public Education | APRIL: Suggested: Council Goals Modification and Fire / EMS; JULY: Did not attend. No committee leadership.; OCTOBER: Suggested: Short-term Rentals, Unsanctioned Camping Code | Suggested: |  |  | Suggested:
Advisory Topics of Interest | Suggested: Succession Planning, HB 2001, Houselessness |  |  | Suggested: Recruitment & Engagement |  |  | Suggested: Climate Friendly & Equitable Communities, Shelter Code | APRIL: Suggested: Shelter Code; SEPTEMBER: Suggested: Short-term Rentals, Unsanctioned Camping Code; NOVEMBER: Suggested: NSSP |  |  | Suggested:
Meeting Presentations | City: Water Systems Master Plan | CANCELED Community Partner: NeighborImpact | City: Strategic Plan, Roadmap, NA Assessment | City: Shelter Code, History of NAs, Recruitment & engagement, Brainstorming Session | City: Recruitment & engagement strategies, Climate Friendly & Equitable Communities, NSSP, DEI Training | None - abbreviated meeting | City: Affordable Housing Tax Exemptions | City: Houselessness in Central Oregon | City: Shelter Code, Revisit NLA Policies/Procedures | City: Shelter Code, Roadmap, Strategic Plan | City: Stevens Road Tract, Deschutes South Canyon, SB 458 | City: City Assesment - CRM Equity & Partnerships | No July Meeting | No August Meeting | New members, Chair vote, extended rep reports, NSSP | Committee: Policies & Procedures
Committee Training/Development Opportunities | [7 empty] | FEBRUARY: CANCELED OSU-Cascades Diversity, Equity & Inclusion Lab #2; MAY: Neighborhoods USA: Sending NLA Rep (Chair Sears); JULY: Terms end- Onboarding new representatives; AUGUST: Terms end- Onboarding new representatives
Identify and support opportunities for collaboration between Neighborhood Associations and the NLA on topics of shared interest. (Goal 2.B.1) |  |  |  | City-hosted Public Info Session on HB 2001 |  |  | NART-hosted Public Info Session on Climate Friendly & Equitable Communities Order | APRIL: NART/Bend Cares-hosted discussions on Houselessness and Shelter Code; OCTOBER: Council Candidate Forum?
Evaluate and adjust committee processes as determined necessary. (Goal 3.D.1) |  |  |  | Mayoral appointment moratorium | Mayoral appointment moratorium | Mayoral appointment moratorium | Mayoral appointment moratorium | FEBRUARY: Mayoral appointment moratorium; MARCH: Decision: New/Revised Appointment Process; OCTOBER: Regular meeting discussion
Begin succession planning, onboarding and leadership handoffs within the committee. (Goal 3.D.3) | Chair/Vice-Chair Resignation Received | New Chair elected | Vice Chair recruitment | New Vice Chair elected |  | Nomination requests | Nomination requests and elections. Revisit meeting time and date. |  | Reminder about term-endings in July | Reminder about term-endings in July | Chair/Vice Chair recruitment | Chair/Vice Chair recruitment | Chair/Vice Chair recruitment | Chair/Vice Chair recruitment | Chair/Vice Chair nominations and vote |  |  |  | Nomination requests and elections. Revisit meeting time and date.
Develop an online NLA handbook, including information on policies and procedures. (Goal 3.D.2) |  |  |  |  | City staff draft handbook | City staff draft handbook | City staff draft handbook | FEBRUARY: City staff draft handbook; MARCH: Presented to NLA, Feedback collected; APRIL: Final
Create a coordinated process for passing along relevant and timely safety information between the Neighborhood Associations and the City. (Goal 1.B.3) | [7 empty] | OCTOBER: Regular meeting discussion
Consider referral of issues that do not meet NLA objectives established by the City Charter to specialized community groups. (Goal 3.D.4) | [7 empty] | OCTOBER: Regular meeting discussion
Land Use / Committee Advocacy
Appoint liaisons to City ad-hoc groups who can report to the Neighborhood Leadership Alliance about efforts and support/input need. (e.g. Wildfire steering committee, Sounding board to house our neighbors, and others). (Goal 3.A.2) |  |  | Visit vacant liaison assignments: Sounding Board to House our Neighbors, NART, Community Building Subcommittee Alternate |  | Visit vacant liaison assignments: NART, Community Building Subcommittee Alternate |  | Visit vacant liaison assignments: Affordable Housing Tax Exemptions, Community Building Subcommittee Alternate | MARCH: Tax Exemptions Group Ends; APRIL: Revisit liaison update format to provide room for more topics of interest on agenda.; SEPTEMBER: Revisit liaison appointments
Understand the impact that each NLA action will have on our community. (Goal 3.C) Understand policy matters up for Council action and provide input to Council using the opportunities provided to advisory committees such as work sessions, submitted letters, public comment and stakeholder groups. (Goal 3.A.1) | Submitted HB 2001 Letter |  |  |  |  | Voted to not weigh in on TBOC recommendations | Agreed to ask for public education on Climate Friendly and Equitable Communities / Voted to have staff liaison provide comment on Shelter Code at PC Work session | FEBRUARY: Voted to submit letter to Planning Commission on Shelter Code amendments.; JULY: Did not attend Council check-in. No committee leadership.; OCTOBER: Participate in roundtable with Council RE: Unsanctioned Camping Code
Facilitate Land Use Education Plan roll out, including time for public input and revision (Goal 1.A.1) | Working Group Wrap-up, Council Check-in Presentation | Last Regular Working Group Meeting, NA Presentations, Webpage Launch | NA Presentations, City Outreach (Facebook, Twitter, Nextdoor, Newsletter) | NA Presentations | NA Presentations | NA Presentations | Neighborhood Associations, Land Use Podcast | FEBRUARY: Ongoing: Presentations
Evaluate impact of recent administrative and code changes to Land Use Notifications (Goal 1.A.2) | [7 empty] | NOVEMBER: Land Use Chair Survey; DECEMBER: Evaluate results of survey | Request to work with City on additional changes at Council Check-in if necessary
Evaluate community knowledge and understanding of land use education plan post roll out, using baseline metrics. (Goal 1.A.3) |  | Set-up website with Feedback and contact form to gather input | [5 empty] | MAY: Job Posting: CDD Communications Person; JULY: Community and Economic Development Department Staff Onboarding; AUGUST: Community and Economic Development Department Staff Onboarding; SEPTEMBER: Community and Economic Development Department Staff Onboarding; NOVEMBER: Land Use Community Survey; DECEMBER: Land Use Community Survey | Evaluate results of survey, Review input received to date from webpage | Develop work plan for creating and revising resources | Revisit with NLA for interest in liaison
Neighborhood Safety
Work with the City to prioritize residential safety projects within the structure of the Neighborhood Street Safety Program. (Goal 1.B.1) | Council Work Begins |  |  |  | NSSP Update | Transportation Bond Oversight Committee makes priority CIP recommendations |  | SEPTEMBER: NSSP Update - Moving forward update; NOVEMBER: est. NSSP grant applications open for round 3
Support collaborative wildfire resiliency education efforts including fire evacuation planning. (Goal 1.B.4) | SB 726 Passed |  |  |  |  | Wildfire Evacuation Presentation? w/ Sheriff's office |  | JUNE: SB 762 Comprehensive Wildfire Risk Mapping Complete; DECEMBER: SB 762 Standards for definsible space set | Adopt SB 726 Standards
Develop process for neighborhood access to Citizen Service Requests (CSRs) and other traffic enforcement data. (Goal 1.B.2) |  | City launches CSR reporting tool |  |  | Ongoing: City looking into different platforms for tracking requests |  |  | JULY: Request 2021 CSR data
Support the City’s efforts with discouraging the use of illegal fireworks and facilitate communications with Neighborhood Associations. (Goal 1.B.2) | Council extends fireworks ban to Aug. 31, discusses permanent fireworks use and sales ban. | Council extends fireworks ban to Dec. 1 |  | City Council votes to ban fireworks | Ongoing: Education about firewoks ban |  |  | APRIL: Design illegal fireworks signs; MAY: Order illegal fireworks signs; JUNE: Distribute Illegal fireworks signs.
Neighborhood Boundaries & Operations
Consider how future and newly annexed areas receive Neighborhood Association representation. (Goal 1.C.1) |  |  |  | City staff and Chair work to get approval from Council to discuss/ Oct. Council Check-in | NLA/NA Survey Open | NLA/NA Survey Closes |  | FEBRUARY: NLA/NA Survey Open; MARCH: NLA/NA Survey Closes; SEPTEMBER: Staff recommends cutting actions related to boundaries. Looking to include a boundaries project in the Neighborhood rebrand.
Work with staff to address potential changes to Neighborhood Association code regarding boundary adjustments. (Goal 1.C.2) |  |  |  | Begin work plan with staff |  |  | View survey results, bring options and results to NLA. | APRIL: Get on code update schedule.; SEPTEMBER: Staff recommends cutting actions related to boundaries. Looking to include a boundaries project in the Neighborhood rebrand.
Gather information on the Neighborhood Association bylaws, board operations, culture, communications, member engagement, etc. in order to identify gaps and offer best practices to support strong and consistent engagement. (Goal 2.A.1) |  |  |  |  | Neighborhood Assessment begins, Communications Survey open | Communications Survey open | Communications Survey closes | FEBRUARY: NA Discussions; MARCH: NA Discussions, Neighborhood Community Survey; APRIL: NA Discussions; SEPTEMBER: Staff recommends cutting actions related to boundaries. Looking to include a boundaries project in the Neighborhood rebrand.
Support the City in its efforts to analyze demographic composition of neighborhoods to improve inclusivity to under-represented communities. (income, ethnicity, language, rent vs. own). (Goal 2.A.2) | [7 empty] | FEBRUARY: CANCELED OSU-Cascades Diversity, Equity & Inclusion Lab #2; MARCH: NA Discussions; APRIL: NA Discussions; SEPTEMBER: Staff recommends cutting actions related to boundaries. Looking to include a boundaries project in the Neighborhood rebrand.
NA Membership Communications & Outreach
Continue presentations and outreach to community groups (i.e. KPOV, Newcomers, Young Professionals etc.). (Goal 2.B.2) | [6 empty] | COCC course highlights neighborhoods, Professor Sarah Baron | FEBRUARY: Leadership Bend Alumni Association Table; MARCH: Outreach to Bend Chamber; APRIL: Bend 101 Event; JULY: Bend 101 Event; OCTOBER: Bend 101 Event
Engage community partners (Visit Bend, LCA, etc.) and collaborate to grow membership. (Goal 2.B.3) |  |  |  |  | City hires Zavi Borja as Community Relations Manager - Equity & Partnerships | City assessment of outreach strategy and structure | City assessment of outreach strategy and structure | FEBRUARY: City assessment of outreach strategy and structure; MARCH: City assessment of outreach strategy and structure; APRIL: City assessment of outreach strategy and structure; MAY: City assessment of outreach strategy and structure; JULY: Alpenglow Park Opening Celebration
Advocate for meaningful community engagement opportunities and processes. (Goal 3.B.1) | NLA Recommendation: HB 2001 Public Education | [5 empty] | Climate Friendly & Equitable Communities Public Education, Shelter Code Public Education | FEBRUARY: Shelter Code Public Education
Work with Human Rights and Equity Commission and other organizations to improve Neighborhood Association outreach and engagement of traditionally under-represented groups (low-income, renters, those experiencing houselessness, and others). (Goal 2.A.3) | [7 empty] | SEPTEMBER: Staff recommends working with Zavi Borja on these items as HREC is still figuring out committee process and priorities. |  |  |  | NA assessment complete and work with HREC begins.
Participate in City diversity, equity and inclusion trainings, in support of City Council goals. (Goal 2.A.4) | [7 empty] | FEBRUARY: CANCELED OSU-Cascades Diversity, Equity & Inclusion Lab #2
Identify best practices, and associated resources required, used by peer cities to engage and inform community members on policy matters. (Goal 3.B.2) | City Neighborhood Assessment | City Neighborhood Assessment | City Neighborhood Assessment | City Neighborhood Assessment | City Neighborhood Assessment | City Neighborhood Assessment | City Neighborhood Assessment | FEBRUARY: City Neighborhood Assessment; MARCH: City Neighborhood Assessment; APRIL: City Neighborhood Assessment; MAY: Neighborhoods USA Conference, Sending NLA member
Support the City in creating additional opportunities for outreach and engagement of the community, using the resources available. (Goal 3.B.3) |  |  |  | Neighborhood Association brochure | Neighborhood Association FAQs | Recruitment & Engagement Plan, Neighborhood Association newsletter launch | Neighborhood Associations, Land Use Podcast | JUNE: Neighborhood Association Booster Video
Note on G24: Makayla Oliver: Need to check on status of this

## Outstanding Topics
TOPIC OF INTEREST | RECOMMENDATION | DATE RECOMMENDED | RECOMMENDING PARTY | STATUS | NOTES
2021-23 COUNCIL GOALS
Neighborhood Assessment | Assess the Neighborhood Association system as a conduit of information and representation and create opportunities to engage under-served communities. | 2021-06-01 | City Council | In Progress | Assessment is being led by Makayla Oliver, Community Relations Manager - Neighborhoods & Civic Engagement.
2021-23 NLA STRATEGIC PLAN ACTIONS
Begin succession planning, onboarding and leadership handoffs within the committee. |  | 2021-06-01 | NLA | In Progress
Identify best practices, and associated resources required, used by peer cities to engage and inform community members on policy matters. | Outreach & Engagement WG | 2021-06-01 | NLA |  | NLA can send one person to NUSA, or working group can take this on as a topic for conversation..
Support the City in creating additional opportunities for outreach and engagement of the community, using the resources available. | Outreach & Engagement WG | 2021-06-01 | NLA |  | Upcoming conversation about policy creation, NLA can play a role in helping guide community engagement.
Create a coordinated process for passing along relevant and timely safety information between the Neighborhood Associations and the City. | Policies & Procedures WG | 2021-06-01 | NLA
Consider referral of issues that do not meet NLA objectives established by the City Charter to specialized community groups. | Policies & Procedures WG | 2021-06-01 | NLA
Evaluate impact of recent changes to land use notifications and public comment. | Land Use WG | 2021-06-01 | NLA | Hold | On hold until Neighborhood Assessment is complete or new CDD Communications staffer is hired.
Evaluate community knowledge and understanding of land use education plan post roll out, using baseline metrics. | Work with new Community Development Staff to transition this project over. | 2021-06-01 | NLA | Hold | On hold until Neighborhood Assessment is complete or new CDD Communications staffer is hired.
Support collaborative wildfire resiliency education efforts including fire evacuation planning. | Shawn McFadden - Summit West NLA representative selected as the liaison to the Wildfire Resiliency Steering Committee. | 2021-06-01 | NLA | Hold | On hold due to State policy activity. Makayla is inquiring about a future NLA presentation on Wildfire Resiliency and upcoming BFR levy.
Consider how future and newly annexed areas receive Neighborhood Association representation. |  | 2021-06-01 | NLA | Hold | Following assessment results.
Work with staff to address potential changes to Neighborhood Association code regarding boundary adjustments. |  | 2021-06-01 | NLA | Hold | Following assessment results.
Work with Human Rights and Equity Commission and other organizations to improve Neighborhood Association outreach and engagement of traditionally under-represented groups (low-income, renters, those experiencing houselessness, and others). | Equity and inclusion director suggested that Makayla present neighborhood assessment results to HREC and ask for direction or input for next steps. | 2021-06-01 | NLA | Hold | Following assessment results.
Develop an online NLA handbook, including information on policies and procedures. | https://www.bendoregon.gov/home/showpublisheddocument/52687/637844243715230000 | 2021-06-01 | NLA | Complete | Makayla has developed a draft handbook for the NLA to review.
Develop process for neighborhood access to Citizen Service Requests (CSRs) and other traffic enforcement data. | https://bendoregon.maps.arcgis.com/apps/dashboards/dc9c1fc633dc43ffa97a87d26b6bd1df | 2021-06-01 | NLA | Complete | CSR dashboard was created to showcase the CSRs received by the City in 2020. Unsure how service requests data will be changing in the future, potential for better data collection platform.
Support the City’s efforts with discouraging the use of illegal fireworks and facilitate communications with Neighborhood Associations. |  | 2021-06-01 | NLA | Complete | Council banned fireworks in October 2021. City will create new yard signs for NAs to distribute.
Participate in City diversity, equity and inclusion trainings, in support of City Council goals. |  | 2021-06-01 | NLA | Complete
Facilitate Land Use Education Plan roll out, including a time for public input and revision. |  | 2021-06-01 | NLA | Complete
Gather information on the Neighborhood Association bylaws, board operations, culture, communications, member engagement, etc. in order to identify gaps and offer best practices to support strong and consistent engagement. |  | 2021-06-01 | NLA | Complete | Makayla is gathering this information in the neighborhood assessment and through compliance forms.
Support the City in its efforts to analyze demographic composition of neighborhoods to improve inclusivity to under-represented communities. (income, ethnicity, language, rent vs. own). |  | 2021-06-01 | NLA | Complete | City staff are in the process of assessing and gathering this data.
2021-23 NEIGHBORHOOD RECRUITMENT & ENGAGEMENT PLAN
Neighborhood Board Roles | NLA comes up with template for board member roles that can be used by NAs. | 2021-11-09 | Recruitment & Engagement Plan |  | Whenever Chair/Vice Chair decide to have it on the agenda. Can go to working group.
Defining meaningful community engagement | NLA discuss engagement process of community and what is meaningful and what is not. Recommendation from Outreach & Engagement WG. | 2021-11-09 | Recruitment & Engagement Plan |  | Whenever Chair/Vice Chair decide to have it on the agenda. Can go to working group.
Defining Neighborhood Association purpose | Purpose in code is to play a role in land use. No community building is mentioned. Does this need to change? | 2021-11-09 | Recruitment & Engagement Plan |  | Following assessment results.
NEIGHBORHOOD ASSOCIATION / COMMUNITY CONCERNS
Bend Tree Code | NLA requested information from City staff on progress and upcoming project. | 2022-03-08 | Southern Crossing NA | In Progress | NLA agreed to getting information about the Bend Tree Code Council Goals Project. Makayla is waiting for staff assigned to the project to return from vacation.
Short-term Rentals | Revisit the topic so NAs are educated on what can and cannot be done about STRs. | 2021-08-30 | Boyd Acres/Cenury West/Old Bend/ Orchard District | In Progress | Council has directed staff to make changes to the program. NLA proposed working group to focus on this topic. Currently looking for NLA rep volunteers.
Public Safety | Look into community member views of Bend PD, review use of force laws and oversight. | 2020-06-09 | Bill Moseley | Interest still? | Response requested from Lt. Juli-Ann McConkey
Deschutes South Canyon | NLA requested to have an informational presentation about this topic from neighborhood leaders, reviewed by Legal | 2022-04-12 | Southern Crossing, Century West, Southwest Bend NAs | Complete | NLA invited Robert Anderson to present on Deschutes South Canyon. Brian Rankin and Colin Stephens were in attendance to speak to UGB process and planning applications.
Climate Friendly & Equitable Communities Rulemaking | Encourage City to host public education about rulemaking efforts. | 2021-12-13 | NART Liaison | Complete | City will work with NART on public info session in January 2022. NLA to support public education about the implementation of EO 20-04 moving forward.
Illegal Fireworks | Yard signs, education, outreach, citations not working. Need a better system for enforcement. | 2020-07-14 | Mountain View NA | Complete | Council banned fireworks in October 2021.
Diversity on boards/committees | Heavily white presence. Let's discuss how to diversify. | 2020-07-14 | Mountain View NA | Complete | City offered OSU-Cascades DEI Lab to all neighborhood leaders.
Visit Bend Business Plan | Neighborhoods should have say in tourism plan for Bend. | 2020-06-09 | Bill Moseley | Complete | Must be written into the contract, look at re-defining involvement for 2021. Potential to start in October for NLA to join conversation about business plan.
Use of non-NLA members to augment NLA work sessions | Subject matter experts should be able to be deputized for work sessions. Example: Planning Commission Work Sessions | 2020-07-14 | David Johnson | Complete | Non-NLA members can not represent the NLA at work sessions or NLA required involvement.
TSP Cut-through Traffic Policy | TSP pushes cut-through traffic into neighborhoods, no policy preventing this. | 2020-06-09 | Bill Moseley | Complete | Addressed. Councilor Mosely made a recommendation to CTAC who approved this request and drafted a policy RE: cut-through traffic that will be adopted with the TSP.
4G/5G Facilities & Cell Towers | What does the City control with these facilities? Health concerns. | 2020-03-10 | Mountain View NA | Complete | NLA received a presentation on 6/9 and informational material to share with NA boards.
LED Street Lights | Street lights are too bright, need shielding or different lumens | 2019-08-13 | Dark Skies CO | Complete | Reviewed. Declined to take action.